## Assumptions
Assumptions
1. Estimations are made based on the Prototype which was showcased earlier
2. This estimations tend to change based on the prototype feedback received from stake holders
3. DevOps related activities will be taken care by Experian
4. Number of developers working on is 8
5. This estimation does not include Regression/Integration Testing & Production Readiness
Overview:
Total Number of sprints required – 5
ACT Sprint # while closing the development – 7

## Estimations
Screen | Section | High Level User Stories | UI -Estimation | BE -Estimation | No of Sprints | ACT Sprint #
|  | Database Schema Preparation and Implementation |  | 5 | 0.3 | Sprint#3
|  | Unit Testing Framework | 8 | 8
Dashboard | Data Cards | API Implementation to get the metrics for 4 data cards | 6 | 5 | 0.4
API Implementation to fetch / Form data for 3 charts
|  | Unit Testing | 4
| Taxonomy History | Taxonomy Progress overview design | 6 | 8 | 0.3
API Implementation for Taxonomy Overview
API Implementation for Taxonomy History
|  | UI- Taxonomy History Grid Functionalities | 3
|  | Unit Testing | 4
| Create Taxonomy | Create new Taxonomy Version By copying prior Taxonomy | 3 | 2 | 2 | Sprint#5
|  | Get Taxonomy Records | 2 | 2
|  | View Audience Segments Data | 4
|  | Edit Audience Segments Data | 6 | 2
|  | Delete Audience Segments Data | 3 | 2
|  | Generate Change history based on User’s input & Display it | 6 | 3
|  | Display Parking Lot data | 4 | 2
|  | Add Parking Lot records to Working Taxonomy | 4 | 2
|  | Adding Validations to the Taxonomy Grid | 8 | 2
|  | Modify Parking lot Data Edit/Delete | 8 | 2
|  | Import New Audiences | 6 | 3
|  | Validation of Imported Audiences | 8 | 2
|  | Add Imported Records to Parking Lot | 4 | 2
|  | Add Imported Records to Working Taxonomy | 4 | 2
|  | Delete an Imported record | 2 | 2
|  | Modify Imported Record | 3 | 2
|  | Add new record to the imported data | 6 | 2
|  | Taxonomy Grid column preferences – Save Preference | 3 | 3
|  | Submit Taxonomy to review [Validations] | 3 | 3
|  | Display Reviewer comments | 3 | 2
|  | Get Drop down Values in Audience Segments Form |  | 2
|  | Form Validations | 4 | 1
|  | Filter grid by new records, modified records etc | 6 | 4
|  | Unit Testing | 10
| Review Taxonomy | Add review Comments for a Audience Segment record | 4 | 2 | 0.4 | Sprint#6
|  | Filters to display only the modified records | 4 | 2
|  | Get all the modified record values to highlight | 3 | 2
|  | Highlight the imported Audience records | 3
|  | Send back for revision Functionality | 2 | 1.5
|  | Approve a Taxonomy Version | 2 | 1.5
|  | Unit Testing | 6
| Export Taxonomy | Get History of Exports | 1 | 2 | 0.2
|  | Generate data file based on Taxonomy Data | 6 | 2
|  | Export Data to S3 buckets | 3
|  | Unit Testing | 4
| Taxonomy Summary | Design Summary page for working Taxonomy | 4 | 2 | 0.1
|  | Unit Testing | 2
Notification | Notification | Notification Page Design | 4 |  | 0.3
|  | Send Notification wherever required [while submitting/revision/approval] | 6
|  | History of notification | 4 | 8
User Profile | Profile | OKTA Authentication | 8 | 2 | 1 | Sprint#7
|  | Login | 4 | 2
|  | Logout | 4 | 2
|  | Session Timeout | 3 | 2
|  | User Not Found | 3 | 2
|  | Role Based Authorization | 8 | 5
|  | Display Logged in User Details | 4 | 2
|  | Add a new User | 6 | 2
|  | Modify an existing user | 4 | 2
|  | Remove user | 2 | 2
|  | Unit Testing | 8
| Data Grid | Implementation of Sorting in Data Grid |  |  | 0.1
Implementation of pagination in Data Grid
Necessary Filters/Search Implementation in Taxonomy History Grid
|  | Delete Multiple Records in all Grids | 6 | 2
| DevOps related Development | Implementing Redis Cache |  | 2 | 0.1
|  | Implementation of Secrets Manager |  | 2
|  | Sonarqube Implementation |  | 2
Regression & Integration Testing
Production Readiness/ Deployment Activities