## Assumptions
Assumptions
1. Estimations are made based on the Prototype which was showcased earlier
2. This estimations tend to change based on the prototype feedback received from stake holders
3. DevOps related activities will be taken care by Experian
4. Number of developers working on is 8
5. This estimation does not include Regression/Integration Testing & Production Readiness
Overview:
Total Number of sprints required – 5
ACT Sprint # while closing the development – 7

## Estimations
Screen | Section | High Level User Stories | Iteration
|  | Database Schema Preparation and Implementation | 1
Unit Testing Framework
Dashboard | Data Cards | API Implementation to get the metrics for data cards | 1
|  | API Implementation to fetch / Form data for charts | 2
|  | Unit Testing | 3
1
| Taxonomy History | API Implementation for Taxonomy History Details | 1
|  | UI- Taxonomy History Grid Functionalities | 1
|  | Implementing Abandoned Functionality | 1
|  | Unit Testing | 3
| Create Taxonomy | Taxonomy Status Management
|  | Create new Taxonomy Version By copying prior Taxonomy | 1
|  | Get Taxonomy Records | 1
|  | View Audience Segments Data | 1
|  | Edit Audience Segments Data | 1
|  | Retire Audience Segments Data | 1
|  | Generate Change history based on User’s input & Display it | 2
|  | Display Parking Lot data | 1
|  | Add Parking Lot records to Working Taxonomy | 1
|  | Adding Validations to the Taxonomy Grid | 1
|  | Edit Parking Lot Data | 1
|  | Delete Parking Lot data | 1
|  | Import New Audiences | 1
|  | Validation of Imported Audiences | 1
|  | View A record from Parking Lot | 1
|  | Delete an Imported record | 1
|  | Modify Imported Record | 1
|  | Manually Add Audiences to Parking Lot & Taxonomy | 1
|  | Taxonomy Grid column preferences – Save Preference | 2
|  | Submit Taxonomy to review [Validations] | 1
|  | Display Reviewer comments | 2
|  | Get Drop down Values in Audience Segments Form | 1
|  | Form Validations | 1
|  | Filter Working Taxonomy grid by new records, modified records etc | 1
|  | Filter Parking Lot grid | 1
|  | Download Data as Excel | 1
|  | Unit Testing | 3
| Review Taxonomy | Add review Comments for a Audience Segment record | 1
|  | Filter records | 1
|  | Get all the modified record values to highlight | 1
|  | Highlight the imported Audience records | 1
|  | Send back for revision Functionality | 1
|  | Approve a Taxonomy Version | 1
|  | Unit Testing | 3
| Export Taxonomy | Get History of Exports | 1
|  | Generate data file based on Taxonomy Data | 2
|  | Setup Background job to execute Export Script | 2
|  | Modify Taxonomy Status | 1
|  | Download exported JSON & Download Grid as Excel | 1
|  | Abandon a Taxonomy | 1
|  | Unit Testing | 4
| Taxonomy Summary | Design Summary page for working Taxonomy | 1
|  | Unit Testing | 4
| Folder Management | Filter Audience Segments based on Folder Infoirmation | 2
|  | Add a new folder | 2
|  | Edit a Folder | 2
|  | Delete Folder | 2
|  | Unit Testing | 4
Notification | Notification | Notification Page Design | 2
|  | Send Notification wherever required [while submitting/revision/approval] | 2
|  | History of notification | 2
|  | Email Sending Based on Taxonomy Status/User Activity | 2
|  | Unit Testing | 4
User Profile | Profile | OKTA Authentication | 2
|  | Login | 1
|  | Logout | 2
|  | User Not Found | 2
|  | Role Based Authorization | 1
|  | Display Logged in User Details | 2
|  | Add a new User | 4
|  | Modify an existing user | 3
|  | Remove user | 3
|  | Unit Testing | 3
| Data Grid | Implementation of Sorting in Data Grid
Implementation of pagination in Data Grid
Necessary Filters/Search Implementation in Taxonomy History Grid
Delete Multiple Records in all Grids
| DevOps related Development | Implementing Redis Cache | 4
|  | Implementation of Secrets Manager | 4
|  | Sonarqube Implementation | 4
| Validation | Validate Add/Edit Audiences | 1
|  | Validate Imported New Audiences | 1
|  | Validate Grid Edit | 1
Regression & Integration Testing
Production Readiness/ Deployment Activities

## Sheet1
Create new Taxonomy Version By copying prior Taxonomy
Get Taxonomy Records
View Audience Segments Data |  |  |  | SP
Edit Audience Segments Data | Import New Audiences | Rajat | NANI 32241 | 2
Delete Audience Segments Data | Validate Imported Audiences | Rajat |  | 3
Generate Change history based on User’s input & Display it | Edit Imported Audiences | Rajat |  | 2
Display Parking Lot data | Delete Imported Audiences | Rajat |  | 2
Add Parking Lot records to Working Taxonomy | View Audience Segments Data | Bhushan |  | 2
Adding Validations to the Taxonomy Grid | Edit Audience Segments Data | Bhushan | NANI 32771 | 2
Modify Parking lot Data Edit/Delete | Delete Audience Segments Data | Bhushan | NANI 32768 | 2
Import New Audiences | Display Reviewer comments | Surya |  | 2
Validation of Imported Audiences | Bulk Delete Audience Segments | Surya |  | 2
Add Imported Records to Parking Lot | Audience Segments Actions Column - Design | Surya |  | 3
Add Imported Records to Working Taxonomy | End User Suggetions in UI Application | Surya/Bhushan/Rajat | NANI 33215 | 3
Delete an Imported record | Validate grid data during Editing
Modify Imported Record
Add new record to the imported data | ability for the user to
Taxonomy Grid column preferences – Save Preference
Submit Taxonomy to review [Validations]
Display Reviewer comments
Get Drop down Values in Audience Segments Form
Form Validations
Filter grid by new records, modified records etc

## Sheet2
Screen | Section | Task
ALL |  | Change Font color as per Experian Style Guide
Dashboard | Cards | Card#1 - Display the count of Audiences in Parking lot. By Clicking the card, the Audience parking list will be displayed.
Card#2 -Display Draft Taxonomy Version with the status [Added/Reviewed/Sent Back for Revision]
Card#3 - Display Active Taxonomy Version and Count of Audiences in the active Taxonomy
Card#4 - Display the no of Archieved Taxonomies and by clicking this card, it will take us to the taxonomy grid which shows the most recent archieved taxonomy, where user can choose any archieved taxonomy version and get the data for it.
| Charts | Chart#1 - Folder fields will be displayed there, and by selecting particular field level details, it will take us to the taxonomy grid, which will have filtered data based on the folder level
Chart#2 - User Personalized data/buttons will be added here
Chart#3 - Change the sub texts in the chart
Taxonomy | Taxonomy History | Create New Taxonomy Button should be changed to resume if a draft taxonomy is created already. By Clicking Resume it will take us to the working step in draft taxonomy.
Taxonomy History Table - Action Column will be added with View [For Active & Archieved Taxonomies], Edit [For Draft Taxonomy]. Clicking the icons will take the user to the particular Taxonomy
| Stepper | Rename the step names to - [In-Progress, Review, Ready to Release, Active]
Provide ability for the user to download the taxonomy as Excel Sheet.
Step#1 - Step 1 will have 2 tabs. Assign Audiences & Add Audiences. The Working Taxonomy grid will come under assign Audiences.
Step#1 - Add Audiences - It will display the parking lot data as grid with Import Audiences button at top. Imported Audiences from excel will be added to the grid.
Step#1 - Move Audiences from Taxonomy to Parking Lot and Vice Versa.
Version Number and Status Fields will be changed as Labelsand position Needs to be adjusted
| Export | Display a table with Previous Export History
Display the sub steps/Progress when we are exporting the data
Enable functionality to download the history data as Excel